## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 84 | 0 |  |  |  | 16 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2016-10-19 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Wed | Fri | Mon | Wed | Fri | Mon | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Wed | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-03 | 2016-10-05 | 2016-10-07 | 2016-10-10 | 2016-10-12 | 2016-10-14 | 2016-10-17 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | [25 empty] | Assigned
6 | [25 empty] | Active
7 | [25 empty] | Verify?
8 | 1 | Come up with an idea | ALL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 1 | Solidify the idea | ALL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | [25 empty] | Fact of Life
11 | [25 empty] | Can't Repro
12 | 1 | Prototyping-1 | ALL |  | 1 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1 | Level | TB |  | 1 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1 | Player Movement | BY |  | 1 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 1 | AI | DE |  | 1 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 1 | Camera | VV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 1 | Simple Main Menu | VV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19
20 | 1 | Prototyping-2 | ALL |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 1 | Vision and Lighting | TB |  | 1 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | Player Collision | BY |  | 3 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 1 | Level Design | VV | BY | 6 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
24
25
26
27 | 1 | Basic Enemy class | DE |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Generic behaviors for enemies
28 | 1 | Sentinel (lazy cat) | DE |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Looks in a circle counterclockwise
29 | 1 | Fat Cat | ALL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | looks in one direction
30 | 1 | Wolf | DE |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | walks back and forth, faster chasing
31 | 1 | Bird | BY |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 2 | Mole | DE |  | 4 | 0 | 2 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pops in and out of mole hills around map, only alerts
33 | 1 | Squirrel | BY |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34
35
36 | 1 | Level Implementation | VV |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 8 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 2 | Modeling + Fine tuning levels+ Bonus level | TB |  | 16 | 0 |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 2 | Music & Sounds | BY |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 8 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 1 | Enemy AI+ bug fixes | DE |  | 8 | 0 |  |  | 8 | 8 | 8 | 8 | 8 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40
41 | [5 empty] | 0 | [8 empty] | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 2 | Extra Levels | ALL |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
43 | 1 | Boss level + testing | VV |  | 4 | 0 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  | Putting together entire implementation | ALL |  | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 |  | Playtesting | ALL |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 |  | Change initial tiles to black instead of invisible | VV |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
108 |  | Moving enemies upon detection | TB |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
109 |  | Dialogue implementations | BY |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
110 |  | Fix the music | BY |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 16 | 16 | 14 | 12 | 9 | 7 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 84 | 84 | 73.5 | 63 | 47.25 | 36.75 | 26.25 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 52 | 52 | 52 | 52 | 52 | 36 | 18.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
216 |  |  | 2 | [5 empty] | 32 | 32 | 32 | 32 | 32 | 24 | 16 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
217 |  |  | 3 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Thomas Bartlett | TB |  |  |  |  | TB | 21 | 21 | 21 | 21 | 21 | 21 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 |  | Venkat Veerappan | VV |  |  |  |  | VV | 17 | 17 | 17 | 17 | 17 | 9 | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
224 |  | Brian Ye | BY |  |  |  |  | BY | 19 | 19 | 19 | 19 | 19 | 11 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 |  | Daniel Engwis | DE |  |  |  |  | DE | 20 | 20 | 20 | 20 | 20 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 17 | 17 | 17 | 17 | 17 | 17 | 9.5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 84
236

## Daily Scrum
Producer | 2016-10-19 |  | Team Members
Approved | Dates |  | Thomas Bartlett | Venkat Veerappan | Brian Ye | Daniel Engwis | All
| 2016-10-03 | Mon | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-04 | Tue | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-05 | Wed | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-06 | Thu | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-07 | Fri | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-08 | Sat | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-09 | Sun | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-10 | Mon | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-11 | Tue | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-12 | Wed | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-13 | Thu | Game Jam | Game Jam | Game Jam | Game Jam
| 2016-10-14 | Fri | Protoyping + building base for game | Designing levels + Enemy types | Doing movement + Music | Creating enemy AI + Enemy movement
| 2016-10-15 | Sat | Modeling + some bug fixes + enemy vision ranges | Added boss level, and implemented remaining levels | Finished music and levels | Fixing bugs with movement, and finishing mole
| 2016-10-16 | Sun | Polishing final game + balancing game | Polishing final game + balancing game | Polishing final game + balancing game | Polishing final game + balancing game
| 2016-10-17 | Mon
| 2016-10-18 | Tue
| 2016-10-19 | Wed
| 2016-10-20 | Thu
| 2016-10-21 | Fri
| 2016-10-22 | Sat
| 2016-10-23 | Sun
| 2016-10-24 | Mon